## Home
SR2515 Project
BMC PVT Test Report
(BMC ver.0.12.00)
Date: 2022/11/01
DBD

## Test Cases
Test Case | BMC Version | Result | Issue Number | Duration (Min) | Plan
|  |  |  | 0 | 24
1. BMC Release Package check
Before testing start, check the BMC file and information first.
1.1 Check package files |  | N/A |  |  | 1
1. Verify BMC files, make sure no file missed.
2. Following the BMC Naming Rule spec to verify the BMC image name, to make sure it is correctly match the spec.
1.2 Check release note |  | N/A |  |  | 1
1. Make sure the readme file in release package or not.
2. Check the detail of readme file, make sure the information is correct.
3. TBD
2. BMC Firmware Flash Test
2.1 Upgrade BMC under RHEL6.5 64 bit OS (Optional) |  | N/A |  |  | 0
1. Boot system into RHEL6.5 X86_64 with all device drivers loaded.
2. Referance readme to update BMC firmware, make sure the firmware can be upgraded and downgraded successfully.
3. After BMC FW flash complete, reboot system. And verify system can boot up normally with no error message.
4. Check BMC firmware version is correct or not under BIOS setup menu.
5. Check BMC firmware version is correct or not from BMC WEB UI.
6. BMC IP address should be changed or missed.
7. BMC MAC address shouldn't be changed or missed.
8. Check BMC SEL, there should be no other unexcepted event.
2.2 Upgrade BMC via WEB UI |  | N/A |  |  | 1
1. Access BMC WEB UI with administrator.
2. Navigate to firmware flash page, check whether BMC FW can be upgraded successfully or not.
3. After BMC FW flash completed, reboot system. And verify system can boot up normally with no error message.
4. Check whether BMC version is correct or not under BIOS setup menu.
5. Verify BMC Version is correct in WEB UI.
6. If not preserve network configure, BMC IP address should be changed or missed .
7. BMC MAC address shouldn't be changed or missed.
8. Check BMC SEL, there should be no other unexcepted event.
3. BMC Basic Function (Basc function and information check)
LAN Configuration for Dedicated NIC port
3.1 LAN Configuration under BIOS setup menu |  | N/A |  |  | 1
1. Boot into BIOS setup menu and enter to BMC LAN setting page.
2. Set BMC port to Dedicated NIC port.
3. Set BMC dedicated port STATIC IP Address. Netmask and Gate way, and verify BMC LAN setting can be saved successfully in BIOS setup.
4. Verify BMC can be accessed via STATIC IP address.
5. Change BMC to DHCP mode, and connect BMC dedicated mgmt port to DHCP server.
6. Verify BMC DHCP IP address, netmask, and gateway can be achieved from DHCP server.
7. Verify BMC can be accessed via DHCP IP address.
FRU
3.2 Check FRU info with the latest BMC Spec and FRU Spec |  | N/A |  |  | 1
1. Verify all device FRU data can be detected successfully by ipmi command (and Web UI)
>ipmitool fru print
SDR
3.3 Sensor Reading |  | N/A |  |  | 1
1. Verify all sensor entries can be listed via SDR command and match with the related sensor spec.
2. Verify all sensor type, sensor ID and sensor reading are correct via SDR command.
USER
3.4 Defualt User name and Password Check |  | N/A |  |  | 1
1. Verify default user name and password can match with BMC Spec definition.
2. Verify BMC and WebUI can be accessed via default user name and password.
3. Verify default user can be enabled and disabled by ipmi command
4. Verify default user (including name string, password, privilege, etc.) can be edited by ipmi command
5. Verify default user (including name string, password, privilege, etc.) can be edited and deleted by WebUI as created another admin level user
Power Control
3.5 Chassis Power control function |  | N/A |  |  | 1
1. Verify the power status match actual status when system is power on and power off.
2. Verify system can power off via power off cmd.
3. Verify system can power on via power on cmd.
4. Verify system can powered cycle via power cycle cmd.
Watchdog Function
3.6 Watchdog Function |  | N/A |  |  | 1
1. Verify POST watchdog can be enabled and disabled in BIOS setup.
2. When POST watchdog is enabled, verify POST Watchdog timer can be edited in BIOS setup. And check if BIOS does not complete POST before the timer expires, the BMC will reset the system. Check BMC SEL will record watchdog event.
3. Verify Watchdog Timer can be reset without any error when system reset.
SOL
3.7 SOL Function |  | N/A |  |  | 1
1. Verify SOL connection can be established successfully with dedicated NIC.
2. Verify Function Key in BIOS Setup Utility of SOL session is work fine
3. Verify SOL functionality can works normally with Redirection After BIOS POST
WebUI
3.8 WebUI Summery Information Check |  | N/A |  |  | 1
1. Check the summury page, verify the FW version, product name, current Date and Time are correcct.
2. Check the NIC configuration page, verify all NIC settings are correct.
3.9 NIC configuration Page（IPv4 and IPv6） |  | N/A |  |  | 1
1. Verify STATIC IP address ,Netmask and Gateway can be set successfully via browser.
2. Verify DHCP IP source can be set successfully via browser and the IP can be used successfully.
3. Verify DNS function.
3.10 SEL Read/Clear |  | N/A |  |  | 1
1. Check SEL page,verify there is no any unexcept event log.
2.Verify SEL event can be cleared and there will be a new log recorded.
3.Type BMC cold reset command,then check there is no unexcept event log
3.11 Sensor Page |  | N/A |  |  | 1
1. Check all sensors' name and SDR data matching with the related release sensor spec in Release Notes
2. Verify all sensors' sensor reading are correct.
3.12 Utility |  | N/A |  |  | 1
1. Verify remote power control function.
1-1. Verify the power control function Power On
1-2. Verify the power control function Power Off Gracefully
1-3. Verify the power control function Power Off Immediately
1-4. Verify the power control function Power Reset
1-5. Verify the power control function Power Cycle
2. Verify resote BMC factory default function.
3.13 PEF |  | N/A |  |  | 1
1. Enable PEF funciton.
2. Configuration and test PEF alerts.
3. Check SNMP and SMTP server can receive message normally
KVM/VM
3.14 KVM/VM Feature Enable and Disable |  |  |  |  | 1
1. Verify KVM/VM function can be enabled wih BMC key.
2. Verify KVM/VM function can be disabled without BMC key.
3.15 KVM Redirection |  | N/A |  |  | 1
1. Verify launch KVM redirection successful without error.
（2. Check the jviewer name and publisher is showed correct ）
3. Verify KVM redirecction via Dedicated NIC port.
4. Verify keyboard and mouse can be sync up with the host server.
5. Verify KVM can support host resolution.
3.16 Virtual Media Mount |  | N/A |  |  | 1
1. Remote mount CD-ROM,IMG file, ISO file, etc.
2. Check virual media status after system reset,DC power loss and AC power loss.
2-1.Virual Media will keep connection after System Reset
2-2.Virual Media will keep connection after DC power loss
2-3.Virual Media will loss connection after AC power loss
3.17 Remote installation OS |  | N/A |  |  | 1
1. Remote install Server OS (List in SWOD,note the latest support OS) via CD-ROM.
2. Verify OS can be installed successfully without any error.
KCS/RMCP/RMCP+ Channel Check
3.18 KCS Interface |  | N/A |  |  | 1
1. Power on system and into DOS mode.
2. Press BMC command (ipmitool 20 18 01) by Ipmitool tool.
3. Check BMC should be response some info by ipmitool tool. (device ID info)
4. Check BMC should be work normal.
3.19 RMCP Interface |  | N/A |  |  | 1
1. Power on system and into DOS mode.
2. Client link SUT by LAN
3. Use ipmitool for Windows under Client.
4. Press BMC command "ipmitool -H SUT's IP -U ADMIN -P hik12345+ raw 0x6 0x1"
5. Check BMC should be response some info by ipmitool tool. (device ID info)
6. Check BMC should be work normal.
3.20 RMCP+ Interface |  | N/A |  |  | 1
1. Power on system and into DOS mode.
2. Client link SUT by LAN
3. Use ipmitool for Windows under Client.
4. Press BMC command "ipmitool -I lanplus -H SUT's IP -U ADMIN -P hik12345+ raw 0x6 0x1"
5. Check BMC should be response some info by ipmitool tool. (device ID info)
6. Check BMC should be work normal.
4. DC Power Cycling
DC cycle
4.1 DC power cycle |  | N/A |  |  | 1
1. Clear BMC log and check system don't have any error or Sensor LED error.
2. Use client remote control by iKVM.
3. Run DC power cycling test overnight. (12hr)
4. Check system should be work normal. (no hang or blue screen or error message)
5. Check BMC event log. ( no cricital , warning , unknow event log)
Note on F6: taouser: Pre-release versino did not have complete files.
Note on F9: taouser: Pre-release versino did not have complete files.

## Feature Update
#Verification
feature Verification
| Issue No. | Title | Result | Version | Note
| 1 | SR2515-303 [powerleader-246&242-BMC]登录bmc界面时，显示的界面默认为中文界面，用户名和密码默认均为ADMIN | Pass | A30803B0006
| 2 | SR2515-302 [powerleader-246&242-BMC]打开bmc登录界面时语言默认为中文 | Pass | A30803B0006
| 3 | SR2515-301 [PowerLeader-246-BIOS]Power Restore Policy 默认为Last State，通电后需等待70s左右才会自动开机，等候时间太长，改为来电10S内开机 | Pass | A30803B0006
| 4 | SR2515-316 [powerleader-242-BIOS]Power Restore Policy 默认为Last State，通电后需等待70s左右才会自动开机，等候时间太长，改为来电10S内开机 | Pass | A30803B0006
| 5 | SR2515-216 [SIT-BMC-246-PowerLeader]bmc中的系统清单如下图，该图片和实物也不相符合，可以把图片去掉，直接文字显示CPU和内存信息就可以，或者图片按实物设计，文字信息显示在图片右边 | Pass | A30803B0006
| 6 | SR2515-196 [SIT-BMC-246-PowerLeader]功耗统计以及环境温度没有字体显示最大值和当前值 | Pass | A30803B0006
| 1 | SR2515-366【Powerleader-BMC】中文界面有部分未汉化完全，插在raid上的硬盘顺序在bmc中显示乱序（LR382A ,LR382F和LR382D都有乱序 | Pass | A30803B0007
| 2 | SR2515-359【Powerleader-BMC】FRU信息中产品信息栏显示的是电源信息，主板信息又不存在了，要求：该页面只显示主板相关信息 | Pass | A30803B0007
| 3 | SR2515-326 [powerleader-BMC]bmc中的系统日志和审计日志无法删除，要求bmc中所有的日志都可以清除，机器在出货前不能有任何日志存在 | Pass | A30803B0007
| 1 | SR2515-426【Powerleader-BMC】可以直接在bmc界面中的FRU信息，那名称后面加上英文缩写，中文界面和英文界面都需要加上英文缩写，看右图范例 | Pass | A30803B0009 | 缩写和FRU工具保持一致
| 2 | SR2515-422【Powerleader-BMC需求】主板的三个网口的mac地址在bmc界面显示，类似于超微那种 | Pass | A30803B0009 | 将BMC mac显示在首页，其他网口在系统清单->网口 下查看
| 3 | SR2515-420【Powerleader-BMC需求】在uefi或者bmc界面更新bios和bmc版本，默认保留原配置信息，如 bmc的ip | Pass | A30803B0009 | 更新BMC版本，默认保留network,inventory.首次刷新需要离线更新 bios更新默认保留配置
| 4 | SR2515-431【Powerleader-BIOS需求】请不要对bios和bmc中的密码的复杂度做任何要求，做到密码可以随意设置的那种 | Pass | A30803B0009 | 添加BMC用户，取消密码复杂度
| 1 | 新增14张PCIE 风扇调测 | pass | A30803B0011
| 2 | 新增IPMI CMD和web UI修改openloop的接口 | pass | A30803B0011 | mode: 0--自动 1--默认 2--低功耗 3--高功耗 4--高性能 get: raw 0x34 0xf8 0 set: raw 0x34 0xf8 1 mode

## Change List
#Verification
Change List Verification
| Issue No. | Title | Result | Version | Note
| NA | NA | N/A | NA | NA
| 1 | 添加CPU功耗以及内存功耗传感器 | Pass | A30803B0007
| 2 | SR2515-391【Powerleader-246-BMC】当使用转速较低的风扇时，bmc界面传感器没有风扇信息，直接提示风扇报警，要求风扇转速高于800转时都为正常 | Pass | A30803B0007 | 修改风扇转速温度传感器的报警阈值为824 rpm
| 3 | SR2515-390【Powerleader-246-BMC】当CPU温度达到100度时，bmc中没任何日志产生，报警灯也不报警，要求：当CPU温度达到100度时，bmc中要产生相关日志，报警灯要报警 | Pass | A30803B0007 | 修改CPU温度传感器的报警阈值为100度
| 4 | SR2515-362【Powerleader-BMC】机器安装有四条内存，但是发现bmc界面传感器中显示所有内存均未插入，或者未做任何操作下突然显示侦测到存在，还伴有日志产生，已经多次出现，现在242和246主板都有发现这个问题 | Pass | A30803B0007 | 修改内存在位状态侦测方式，废弃原来BIOS汇报方式，改为BMC主动侦测，
| 5 | SR2515-367【POwerleader-BMC】DIMM0,1,2,3这样写分辨不出每条内存实际对应的内存物理位置，DIMM0,1,2,3插槽用DIMMA1,A2,B1,B2和实际插槽一一对应,中文界面也未汉化这里 | Pass | A30803B0007
| 6 | SR2515-366【Powerleader-BMC】中文界面有部分未汉化完全，插在raid上的硬盘顺序在bmc中显示乱序（LR382A ,LR382F和LR382D都有乱序 | Pass | A30803B0007 | 按照编号排序
| 7 | SR2515-393【powerleader-246/242-EE】C242和C246主板搭配勤诚1U4盘位机箱时，报警灯在任何情况下都不报警 | Pass | A30803B0007 | 按照硬件要求调整报警LED的GPIO pin
| 8 | SR2515-378 [SIT-BMC-246-1U] WEBUI-IPMI事件日志中按照类型筛选选择PEF_Action没有日志显示 | Pass | A30803B0007 | PEF_Action 和 BMC_Time 合并为一个sensor "BMC_System"；时间同步以及PEF action 的SEL都记录在"BMC_System"下
| 1 | SR2515-409 [SIT-BMC-246-2U/1U] 机器健康状态下，BMC Webui健康状态LED显示为绿色但是前面板报警灯一直显示为红色 | Pass | A30803B0008 | 07版BMC控制LED灯的设计不能同时适配新老面板，08版BMC同时控制新老面板的LED灯对应的GPIO灯，因此无论是新面板还是老面板，LED报警灯功能都可以正常工作
| 1 | 增加 CPU process Throttled sel log | Pass | A30803B0009 | 侦测CPLD信号，GPIO信号拉高触发log,健康状态灯闪烁
| 2 | SR2515-425【Powerleader-BMC】内存在传感器名称为 S_CPU_CH_A1，在一般传感器名称为DIMM_A_1，需要统一名称，不要写CPU，使用DIMM 名称上需要有DIMM A1 /A2/B1/B2，还有bios中的内存信息也用DIMM A1 /A2/B1/B2来表述 | Pass | A30803B0009 | S_CPU_CH_A1/A2/B1/B2修改States_DIMM_A1/A2/B1/B2 T_DIMM_A_1/A_2/B_1/B_2修改Temp_DIMM_A1/A2/B1/B2

## Issue Verification
#Verification
Defect Verification
| Issue No. | Title | Result | Version | Note
| NA | NA | N/A | NA | NA
| 1 | SR2515-89 设置一个BMC_Reset会触发机器power cycle的PEF，当触发这个PEF后机器为power off状态 | Pass | A30803B0003
| 2 | SR2515-35 BMC log中报错PVCC_CPU电压异常 | Pass | A30803B0003
| 3 | SR2515-179 BMC不能准确读取内存温度 | Pass | A30803B0003
| 4 | SR2515-68 BMC读取到的内存数量与实际安装内存数量不符 | Pass | A30803B0003
| 5 | SR2515-138 设置为JBOD模式PD状态在webui显示为Failed | Pass | A30803B0003
| 6 | SR2515-155 BMC WEBUI设置风扇为Full Mode 需要保存两次生效 | Pass | A30803B0003
| 7 | SR2515-147 fan4 插槽fan duty 读取错误 | Pass | A30803B0003
| 8 | SR2515-182 SEL记录更新BIOS的日志为“Version Change#0x89” | Pass | A30803B0003
| 9 | SR2515-77 BMC不能准确读取到部分sensor的信息 | Pass | A30803B0003
| 10 | SR2515-170 部分sensor thresholds不符合规范 | Pass | A30803B0003
| 11 | SR2515-207 Ambilent sensor监控不到进风口sensor温度 | Pass | A30803B0003
| 1 | SR2515-246 [SIT-BMC-246-2U] KVM右上角的通知，不能显示具体通知内容 | Pass | A30803B0004
| 2 | SR2515-236 [SIT-BMC-246-2U] WEBUI中按日期筛选日志，会显示指定时间段外的日志 | Pass | A30803B0004
| 3 | SR2515-233 [SIT-BMC-246-2U] 拔掉1+1冗余电源的其中一个电源，BMC还可以读到两个电源信息 | Pass | A30803B0004
| 4 | SR2515-227 [SIT-BMC-246-2U] sdr部分信息显示顺序乱 | Pass | A30803B0004
| 5 | SR2515-226 [SIT-BMC-246-2U] 前背板sensor名称显示为RearBP | Pass | A30803B0004
| 6 | SR2515-222 [SIT-BMC-246-2U]WEBUI中关键传感器没有报错但是健康状态为红色 | Pass | A30803B0004
| 7 | SR2515-200 [SIT-BMC-246-PowerLeader] 在不安装阵列卡的情况下界面右上角的报警信息错误，见图 | Pass | A30803B0004
| 8 | SR2515-195 [SIT-BIOS-246_PowerLeader] Power Restore Policy 默认为Last State | Pass | A30803B0004
| 9 | SR2515-191 [SIT-BMC-246-PowerLeader]开关板中的报警灯一直常亮红色灯 | Pass | A30803B0004
| 10 | SR2515-145 [SIT-BMC-246-2U] BMC WEBUI系统清单中PCIE卡部分信息显示不正确 | Pass | A30803B0004
| 11 | SR2515-144 [SIT-BMC-246-2U] BMC SEL没有关于PSU的日志记录 | Pass | A30803B0004
| 12 | SR2515-143 [SIT-BMC-246-2U] BMC SDR没有PSU2_state和PSU_Redundancy信息 | Pass | A30803B0004
| 13 | SR2515-133 [SIT-BMC-246-2U] KVM服务允许最大会话数为4，但是打开第二个KVM授予权限后KVM会提示网络连接丢失 | Pass | A30803B0004
| 14 | SR2515-110 [SIT-BMC-246-2U] 在Web上选择“保留配置-IPMI”选项后，刷新BMC FW后不会清除旧的BMC日志 | Pass | A30803B0004
| 15 | SR2515-108 [SIT-BMC-242-1U] BMC webui设置为中文模式，部分信息显示不正确 | Pass | A30803B0004
| 16 | SR2515-91 [SIT-BMC-242-1U] 使用管理员权限的用户ID3登录WEBUI，不能修改用户ID2的默认用户名 | Pass | A30803B0004
| 17 | SR2515-78 [SIT-BMC-242-2U] 机器处于关机状态时BMC webui health led显示为红色闪烁 | Pass | A30803B0004
| 18 | SR2515-198 [SIT-BMC-246-PowerLeader]主板风扇不接满的话，关键传感器那里一直有风扇报错 | Pass | A30803B0004
| 19 | SR2515-171 [SIT-BMC-246-2U] 移除Fan4后BMC不会报错 | Pass | A30803B0004
| 20 | SR2515-242 [SIT-BMC-246-PowerLeader]红框中的汉化只出现过一次中文，汉化也有错误信息，其他时间全部为英文 | Pass | A30803B0004
| 21 | SR2515-243 [SIT-BMC-246-PowerLeader] bmc中离散传感器的某些项全部和硬盘有关 | Pass | A30803B0004
| 22 | SR2515-259 [SIT-BMC-246-2U] PVCC_CPU的值不在正常阀值范围内BMC没有报错 | Pass | A30803B0004
| 23 | SR2515-257 [SIT-EE-246-2U] BMC读取到P3V_BAT为0 Volts | Pass | A30803B0004
| 24 | SR2515-89 [SIT-BMC-242-1U] 设置一个BMC_Reset会触发机器power cycle的PEF，当触发这个PEF后机器为power off状态 | Pass | A30803B0004
| 1 | SR2515-292 [SIT_BMC_246_1U]MSI 101B 在BMC webUI inventory 显示的device name为HAMLIN_ANDROS与BIOS里显示不一致 | Pass | A30803B0005
| 2 | SR2201-290 [SIT-BMC-246-2U] GPU卡与显卡在webui显示的设备名称为undefined | Pass | A30803B0005
| 3 | SR2201-289 [SIT-BMC-246-2U] 1+1冗余电源只安装一个电源模块BMC没有报警 | Pass | A30803B0005
| 4 | SR2201-288 [SIT-BMC-246-2U] BMC有关于风扇转速过低的报警 | Pass | A30803B0005
| 5 | SR2201-249 [SIT-BIOS-246-2U]SMBIOS信息中不显示type39信息 | Pass | A30803B0005
| 6 | SR2201-238 [SIT-BMC-246-PowerLeader]不管接多少块硬盘，Bmc中的离散传感器中只有HDD0~3信息，且一直显示正常状态， | Pass | A30803B0005
| 7 | SR2201-204 [SIT-BMC-1U-246]使用ITP工具对CPU进行注错后，BMC log中无记录。 | Pass | A30803B0005
| 8 | SR2201-107 [SIT-BMC-242-1U] 在“维护-还原配置”选择上传之前下载的文件会提示“恢复备份配置时发生错误”，但是配置信息已成功还原 | Pass | A30803B0005
| 9 | SR2201-100 [SIT-BMC-246-1U] 前UID 灯不亮 | Pass | A30803B0005
| 10 | SR2515-286 [SIT-BMC-246-2U] 外接raid卡replacing时webui中PD state显示为7 | Pass | A30803B0005
| 11 | SR2515-293 [SIT-BMC-242-1U]按压UID button7秒钟以上BMC不会重启 | Pass | A30803B0005
| 12 | SR2515-258 [SIT-BMC-246-2U] BMC读取到VR_Temp_GT为0并且BMC没有报错 | Pass | A30803B0005
| 13 | SR2515-193 [SIT-BMC-246-PowerLeader]关键传感器那里一直有报错信息 | Pass | A30803B0005
| 14 | SR2515-163 [SIT-BMC-242-1U] 运行AC cycle期间BMC日志时间显示为“Pre-Init” | Pass | A30803B0005
| 1 | SR2515-329 [powerleader-BMC]冗余电源都插进去，其中一个电源模块不通电，bmc中还是显示两个模块正常，如沟通，在开机运行时，不插模块时显示一种状态，插模块后不通电显示另外一种状态，只有在插模块通电才显示Normal状态 | Pass | A30803B0006
| 2 | SR2515-328 [powerleader-BMC]前面板报警灯在电源，风扇等硬件发生变化得情况下，报警灯无报警指示，硬盘在做了阵列之后拔掉报警灯才会报警 | Pass | A30803B0006
| 3 | SR2515-319 [SIT-BMC-246-2U] 配置传感器名称为内存温度/P1V2_BMC_AUX_SEN/State_Host_Power的PEF， 保存后显示未配置 | Pass | A30803B0006
| 4 | SR2515-318 [SIT_BMC_242&246_1U&2U]BMC Inventory 显示的i350-T2网卡的name与bios下不一致 | Pass | A30803B0006
| 5 | SR2515-312 [powerleader-242-BMC]bmc中的FRU信息，1处的机箱信息取消掉，2处的全部为中文，3处序号全部改为序列号，4处的型号改为我们公司提供的主板型号 | Pass | A30803B0006
| 6 | SR2515-295 [SIT-BMC-246-2U] 更改PVCC_CPU sensor阀值触发unr错误没有日志记录 | Pass | A30803B0006
| 7 | SR2515-230 [SIT-BMC-246-2U] 通过BMC更新BIOS FW失败 | Pass | A30803B0006
| 8 | SR2515-134 [SIT-BMC-246-2U] SEL日志中没有关于RAID rebuild的日志记录 | Pass | A30803B0006
| 9 | SR2515-348 [Poweleader-BMC-242]主板上只有两个PCIE插槽，但是bmc界面系统清单中显示有三个PCIE路径 | Pass | A30803B0006
| 1 | SR2515-352 [SIT-BMC-246-2U] 在BMC WEBUI更改FRU信息保存失败 | Pass | A30803B0007
| 2 | SR2515-353 [SIT-BMC-246-2U] 中文模式下webui登录界面“更改语言”显示为英语 | Pass | A30803B0007
| 3 | SR2515-365 [SIT-BMC-246-1U/2U] HDD fault状态前面板LED未报警 | Pass | A30803B0007
| 4 | SR2515-377 [SIT-BMC-246-1U] WEBUI-系统日志按照事件种类筛选后日志总数为当前显示数 | Pass | A30803B0007
| 5 | SR2515-358【Powerleader-BMC】以前正常识别的网卡设备在06版bmc下无法识别，只能识别到该槽位有PCI设备 | Pass | A30803B0007
| 1 | SR2515-410 [SIT-BMC-246-2U] BMC Webui显示问题及BMC release 包中的显示问题 | Pass | A30803B0008 | 1.将DIMM inventory 的显示修改为 DIMM A1/B1 DIMM A2/B2 2.将inventory PCIE 设备路径 PCH_PEG5_SLOT2修改为PCH_PE5_SLOT2以匹配主板丝印
| 1 | SR2515-413[SIT-BMC-246-2U] Webui inventory中显示9311-8i的设备名称为INDIANFARMS | Pass | A30803B0009
| 2 | SR2515-412 [SIT-BMC-246-2U] RAID管理-物理设备信息中硬盘温度读取错误 | Pass | A30803B0009
| 3 | SR2515-407 [SIT-BIOS-246-2U] 在webui更新BIOS固件时选择保存配置提示更新成功但是实际版本没有变化 | Pass | A30803B0009
| 4 | SR2515-414 [SIT-BMC-246-2U]java KVM中虚拟USB设置为8GB，OS下只显示3.8GB | Pass | A30803B0009
| 1 | 上下电过程中，BMC flash 被串写，导致BMC无法正常启动 | Pass | A30803B0010
| 1 | [SIT-BIOS-242/246]BIOS下打开任意一个COM口，Windows下都没有Ports（COM&LPT）显示 | pass | A30803B0012

## test Issuse Verification (hidden)
#Verification
Defect Verification
| Issue No. | Title | Config | Result | Duration | Note
Change List Verification
| No. | Feature | Config | Result | Duration | Influence